## Resumo
Nome do estudante		Ryan Lazaretti Ramos
Número do programa #		Programa 2
Nome do programa		ContadorLinhas					Program	LOC Counter					Program#		2A				Program	Linear Regression					Program#		3A				Program	Numerical Integration					Program#		4A				Program	Sort					Program#		5A				Program	Prediction Interval					Program#		6A				Program	Chi-square Test					Program#		7A				Program	Multiple Regression					Program#		8A				Program	Chi-square Test					Program#		9A				Program	Multiple Regression					Program#		10A					Formulas
Linguagem de programação		Java					Instructor	0					Language		0				Instructor	0					Language		0				Instructor	0					Language		0				Instructor	0					Language		0				Instructor	0					Language		0				Instructor	0					Language		0				Instructor	0					Language		0				Instructor	0					Language		0				Instructor	0					Language		0					1		0	320	490		1		48		42				270				10		90		30		1		0				0				0		0		0		0				0				0		0
							2	0	0	0	0		0	0	0	0	0			0	0			0	0	0	0	0	0		0		0				0				0		0		0		0				0				0		0
Resumo		Planejado		Efetivo		Até agora
Tamanho		320		490

		Planejado		Efetivo		Até agora		Até agora %					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					#REF!	#REF!	3	#REF!	0	#REF!	0		0	0	0	0	0			0	0			0	0	0	0	0	0		0		0				0				0		0		0		0				0				0		0
Tempo na fase (min.)							Program Size (LOC)					Summary					Summary					Summary					Summary					Summary					Summary					Summary					Summary					#REF!	#REF!	4	#REF!	0	#REF!	0		0	#REF!	0	#REF!	0			#REF!	0			#REF!	0	#REF!	0	#REF!	0		0		0				0				0		0		0		0				0				0		0
Planejamento		30		48		48		9,8				Base(B)				?????					LOC/Hour		?????		?????		?????					LOC/Hour		#REF!		0,0		#REF!					LOC/Hour		0,0		0,0		0,0					LOC/Hour		#REF!		0,0		0,0					LOC/Hour		#REF!		0,0		0,0					LOC/Hour		#REF!		0,0		0,0					LOC/Hour		#REF!		0,00		0,00					LOC/Hour		#REF!		0,00		0,00					#REF!	#REF!	5	#REF!	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
Projeto		30		42		42		8,6				Deleted(D)				?????					Planned Time		#REF!				?????					Planned Time		0				0					Planned Time		#REF!				#REF!					Planned Time		#REF!				#REF!					Planned Time		#REF!				#REF!					Planned Time		#REF!				#REF!					Planned Time		#REF!				#REF!					#REF!	#REF!	6	#REF!	0	#REF!	0	0	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0
Codificação		180		270		270		55,1				Modified(M)				?????					Program Size (LOC)					Actual Time				0		?????					Actual Time				0		0					Actual Time				0		0					Actual Time				0		0					Actual Time				0		0					Actual Time				0		0					Actual Time				0		0					#REF!	#REF!	7	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0
Compilação		10		10		10		2,0				Added(A)				?????					Base(B)		#REF!		#REF!					CPI (Planned/Actual Time)					?????					CPI (Planned/Actual Time)					0,00					CPI (Planned/Actual Time)					0,00					CPI (Planned/Actual Time)					0,00					CPI (Planned/Actual Time)					0,00					CPI (Planned/Actual Time)					0,00					CPI (Planned/Actual Time)					0,00					#REF!	#REF!	8	#REF!	0	#REF!	0	0,0	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0
Teste		60		90		90		18,4				Reused(R)				?????		?????					Deleted(D)		#REF!		#REF!					% Reused		?????		?????		?????					% Reused		#REF!		0,0		0,0					% Reused		#REF!		0,0		0,0					% Reused		#REF!		0,0		0,0					% Reused		#REF!		0,0		0,0					% Reused		#REF!		0,0		0,0					% Reused		#REF!		0,0		0,0					#REF!	#REF!	9	#REF!	0	#REF!	0	0,0	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0
Encerramento		10		30		30		6,1				Total N&C (N)		?????		?????		?????					Modified(M)		#REF!		#REF!					% New Reused		?????		?????		?????					% New Reused		#REF!		#REF!		#REF!					% New Reused		#REF!		#REF!		#REF!					% New Reused		#REF!		#REF!		#REF!					% New Reused		#REF!		#REF!		#REF!					% New Reused		#REF!		#REF!		#REF!					% New Reused		#REF!		#REF!		#REF!					#REF!	#REF!	10	#REF!	0	#REF!	0	0,0	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0
Tempo total		320,0		490		490	0	100,0				Total LOC(T)				?????		?????					Added(A)		#REF!		#REF!					Test Defects/KLOC		?????		?????		?????					Test Defects/KLOC		#REF!		#REF!		#REF!					Test Defects/KLOC		#REF!		#REF!		#REF!					Test Defects/KLOC		#REF!		#REF!		#REF!					Test Defects/KLOC		#REF!		#REF!		#REF!					Test Defects/KLOC		#REF!		#REF!		#REF!					#REF!	#REF!	Totals	#REF!	0	#REF!	490	#REF!	1	#REF!	48	#REF!	42	#REF!	0	#REF!	270	#REF!	0	#REF!	10	#REF!	90	#REF!	30	#REF!	1	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0	#REF!	0
							Total New Reused				?????		?????					Reused(R)		#REF!		#REF!		#REF!					Program Size (LOC)					Total Defects/KLOC		?????		?????		?????					Total Defects/KLOC		#REF!		#REF!		#REF!					Total Defects/KLOC		#REF!		#REF!		#REF!					Total Defects/KLOC		#REF!		#REF!		#REF!					Total Defects/KLOC		#REF!		#REF!		#REF!					Total Defects/KLOC		#REF!		#REF!		#REF!
Defeitos inseridos							Total N&C (N)		#REF!		#REF!		#REF!					Base(B)		#REF!		#REF!					Yield %		?????		?????		?????					Yield %		#REF!		100,0		100,0					Yield %		#REF!		100,0		100,0					Yield %		#REF!		100,0		100,0					Yield %		#REF!		100,0		100,0					Yield %		#REF!		100,0		100,0
Planejamento				1		1		100,0				Time in Phase (min.)					Total LOC(T)		#REF!		?????		0					Deleted(D)		#REF!		#REF!					% Appraisal COQ		?????		?????		?????					% Appraisal COQ		#REF!		0,0		0,0					% Appraisal COQ		#REF!		0,0		0,0					% Appraisal COQ		#REF!		0,0		0,0					% Appraisal COQ		#REF!		0,0		0,0
Projeto				0		0		0,0				Planning		?????		0		48		9,8				Total New Reused		#REF!		Erro:504		Erro:504					Modified(M)		#REF!		#REF!					Program Size (LOC)					% Failure COQ		?????		?????		?????					% Failure COQ		#REF!		0,0		0,0					% Failure COQ		#REF!		0,0		0,0					% Failure COQ		#REF!		0,0		0,0					% Failure COQ		#REF!		0,0		0,0
Codificação				0		0		0,0				Design		?????		0		42		8,6				Total Object LOC(E)		#REF!		#REF!		#REF!					Added(A)		#REF!		#REF!					Base(B)		#REF!		#REF!					COQ A/F Ratio		?????		?????		?????					COQ A/F Ratio		#REF!		0,00		0,00					COQ A/F Ratio		#REF!		0,00		0,00					COQ A/F Ratio		#REF!		0,00		0,00					COQ A/F Ratio		#REF!		0,00		0,00
Compilação				0		0		0,0				Code		?????		0		270		55,1					Reused(R)		#REF!		#REF!		#REF!					Deleted(D)		#REF!		#REF!
Teste				0		0		0,0				Compile		?????		0		10		2,0				Time in Phase (min.)					Total N&C (N)		#REF!		#REF!		#REF!					Modified(M)		#REF!		#REF!					Program Size (LOC)					Program Size (LOC)					Program Size (LOC)					Program Size (LOC)					Program Size (LOC)
Total de defeitos inseridos				1		1	0	100,0				Test		?????		0		90		18,4				Planning		#REF!		0		48		9,8				Total LOC(T)		#REF!		?????		0					Added(A)		#REF!		#REF!					Base(B)		#REF!		#REF!					Base(B)		#REF!		#REF!					Base(B)		#REF!		#REF!					Base(B)		#REF!		#REF!					Base(B)		#REF!		#REF!
							Postmortem		?????		0		30		6,1				Design		#REF!		0		42		8,6				Total New Reused		#REF!		Erro:504		Erro:504					Reused(R)		#REF!		#REF!		#REF!					Deleted(D)		#REF!		#REF!					Deleted(D)		#REF!		#REF!					Deleted(D)		#REF!		#REF!					Deleted(D)		#REF!		#REF!					Deleted(D)		#REF!		#REF!
Defeitos corrigidos							Total		?????		0		490		100,0				Code		#REF!		0		270		55,1				Total Object LOC(E)		#REF!		#REF!		#REF!					Total N&C (N)		#REF!		#REF!		#REF!					Modified(M)		#REF!		#REF!					Modified(M)		#REF!		#REF!					Modified(M)		#REF!		#REF!					Modified(M)		#REF!		#REF!					Modified(M)		#REF!		#REF!
Planejamento				0		0		0,0					Compile		#REF!		0		10		2,0					Total LOC(T)		#REF!		?????		0					Added(A)		#REF!		#REF!					Added(A)		#REF!		#REF!					Added(A)		#REF!		#REF!					Added(A)		#REF!		#REF!					Added(A)		#REF!		#REF!
Projeto				0		0		0,0				Defects Injected					Test		#REF!		0		90		18,4				Time in Phase (min.)					Total New Reused		#REF!		Erro:504		Erro:504					Reused(R)		#REF!		#REF!		#REF!					Reused(R)		#REF!		#REF!		#REF!					Reused(R)		#REF!		#REF!		#REF!					Reused(R)		#REF!		#REF!		#REF!					Reused(R)		#REF!		#REF!		#REF!
Codificação				0		0		0,0				Planning				0		1		100,0				Postmortem		#REF!		0		30		6,1				Planning		#REF!		0		48		9,8				Total Object LOC(E)		#REF!		#REF!		#REF!					Total N&C (N)		#REF!		#REF!		#REF!					Total N&C (N)		#REF!		#REF!		#REF!					Total N&C (N)		#REF!		#REF!		#REF!					Total N&C (N)		#REF!		#REF!		#REF!					Total N&C (N)		#REF!		#REF!		#REF!
Compilação				0		0		0,0				Design				0		0		0,0				Total		#REF!		0		490		100,0				Design		#REF!		0		42		8,6				UPI (70%)		#REF!					Total LOC(T)		#REF!		?????		0					Total LOC(T)		#REF!		?????		0					Total LOC(T)		#REF!		?????		0					Total LOC(T)		#REF!		?????		0					Total LOC(T)		#REF!		?????		0
Teste				0		0		0,0				Code				0		0		0,0					Code		#REF!		0		270		55,1				LPI (70%)		#REF!					Total New Reused		#REF!		Erro:504		Erro:504					Total New Reused		#REF!		Erro:504		Erro:504					Total New Reused		#REF!		Erro:504		Erro:504					Total New Reused		#REF!		Erro:504		Erro:504					Total New Reused		#REF!		Erro:504		Erro:504
Total de defeitos corrigidos				0		0	0	0,0				Compile				0		0		0,0				Defects Injected					Compile		#REF!		0		10		2,0					Total Object LOC(E)		#REF!		#REF!		#REF!					Total Object LOC(E)		#REF!		#REF!		#REF!					Total Object LOC(E)		#REF!		#REF!		#REF!					Total Object LOC(E)		#REF!		#REF!		#REF!					Total Object LOC(E)		#REF!		#REF!		#REF!
Defeitos encontrados após entrega				?????		?????					Test				0		0		0,0				Planning				0		1		100,0				Test		#REF!		0		90		18,4				Time in Phase (min.)					UPI (70%)		#REF!					UPI (70%)		#REF!					UPI (70%)		#REF!					UPI (70%)		#REF!					UPI (70%)		#REF!
							Total Development				0		1		100,0				Design				0		0		0,0				Postmortem		#REF!		0		30		6,1				Planning		?????		0		0		0,0				LPI (70%)		#REF!					LPI (70%)		#REF!					LPI (70%)		#REF!					LPI (70%)		#REF!					LPI (70%)		#REF!
							Code				0		0		0,0				Total		#REF!		0		490		100,0				Design		?????		0		0		0,0
							Defects Removed					Compile				0		0		0,0					Design Review		?????		0		0		0,0				Time in Phase (min.)					Time in Phase (min.)					Time in Phase (min.)					Time in Phase (min.)					Time in Phase (min.)
							Planning				0		0		0,0				Test				0		0		0,0				Defects Injected					Code		?????		0		0		0,0				Planning		#REF!		0		0		0,0				Planning		#REF!		0		0		0,0				Planning		#REF!		0		0		0,0				Planning		#REF!		0		0		0,0				Planning		#REF!		0		0		0,0
							Design				0		0		0,0				Total Development				0		1		100,0				Planning				0		1		100,0				Code Review		?????		0		0		0,0				Design		#REF!		0		0		0,0				Design		#REF!		0		0		0,0				Design		#REF!		0		0		0,0				Design		#REF!		0		0		0,0				High-level Design		0		0		0		0,0
							Code				0		0		0,0					Design				0		0		0,0				Compile		?????		0		0		0,0				Design Review		#REF!		0		0		0,0				Design Review		#REF!		0		0		0,0				Design Review		#REF!		0		0		0,0				Design Review		#REF!		0		0		0,0				HLDR		0		0		0		0,0
							Compile				0		0		0,0				Defects Removed					Code				0		0		0,0				Test		?????		0		0		0,0				Code		#REF!		0		0		0,0				Code		#REF!		0		0		0,0				Code		#REF!		0		0		0,0				Code		#REF!		0		0		0,0				Design		#REF!		0		0		0,0
							Test				0		0		0,0				Planning				0		0		0,0				Compile				0		0		0,0				Postmortem		?????		0		0		0,0				Code Review		#REF!		0		0		0,0				Code Review		#REF!		0		0		0,0				Code Review		#REF!		0		0		0,0				Code Review		#REF!		0		0		0,0				Design Review		#REF!		0		0		0,0
							Total Development				0		0		0,0				Design				0		0		0,0				Test				0		0		0,0				Total		?????		0		0		0,0				Compile		#REF!		0		0		0,0				Compile		#REF!		0		0		0,0				Compile		#REF!		0		0		0,0				Compile		#REF!		0		0		0,0				Code		#REF!		0		0		0,0
							After Development				?????		?????					Code				0		0		0,0				Total Development				0		1		100,0				UPI (70%)		?????					Test		#REF!		0		0		0,0				Test		#REF!		0		0		0,0				Test		#REF!		0		0		0,0				Test		#REF!		0		0		0,0				Code Review		#REF!		0		0		0,0
							Compile				0		0		0,0					LPI (70%)		?????					Postmortem		#REF!		0		0		0,0				Postmortem		#REF!		0		0		0,0				Postmortem		#REF!		0		0		0,0				Postmortem		#REF!		0		0		0,0				Compile		#REF!		0		0		0,0
							Test				0		0		0,0				Defects Removed					Total		#REF!		0		0		0,0				Total		#REF!		0		0		0,0				Total		#REF!		0		0		0,0				Total		#REF!		0		0		0,0				Test		#REF!		0		0		0,0
							Total Development				0		0		0,0				Planning				0		0		0,0					UPI (70%)		#REF!					UPI (70%)		#REF!					UPI (70%)		#REF!					UPI (70%)		#REF!					Postmortem		#REF!		0		0		0,0
							After Development				?????		?????					Design				0		0		0,0					LPI (70%)		#REF!					LPI (70%)		#REF!					LPI (70%)		#REF!					LPI (70%)		#REF!					Total		#REF!		0		0		0,0
							Code				0		0		0,0					UPI (70%)		#REF!
							Compile				0		0		0,0					LPI (70%)		#REF!
							Test				0		0		0,0
							Total Development				0		0		0,0
							After Development				?????		?????

							PSP2 Project Plan Summary - Program 5A (Continued)					PSP2.1 Project Plan Summary - Program 6A (Continued)					PSP2.1 Project Plan Summary - Program 7A (Continued)					PSP2.1 Project Plan Summary - Program 8A (Continued)					PSP2.1 Project Plan Summary - Program 9A (Continued)					PSP3 Project Plan Summary - Program 10A (Continued)

							Student	0					Date		30/12/1899				Student	0					Date		30/12/1899				Student	0					Date		30/12/1899				Student	0					Date		30/12/1899				Student	0					Date		30/12/1899				Student	0					Date		30/12/1899
							Program	Sort					Program#		5A				Program	Prediction Interval					Program#		6A				Program	Chi-square Test					Program#		7A				Program	List Sort					Program#		8A				Program	Chi-square Test					Program#		9A				Program	Multiple Regression					Program#		10A
							Instructor	0					Language		0				Instructor	0					Language		0				Instructor	0					Language		0				Instructor	0					Language		0				Instructor	0					Language		0				Instructor	0					Language		0

							Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%
							Defects Injected					Defects Injected					Defects Injected					Defects Injected					Defects Injected					Defects Injected
							Planning		?????		0		0		0,0				Planning		#REF!		0		0		0,0				Planning		#REF!		0		0		0,0				Planning		#REF!		0		0		0,0				Planning		#REF!		0		0		0,0				Planning		#REF!		0		0		0,0
							Design		?????		0		0		0,0				Design		#REF!		0		0		0,0				Design		#REF!		0		0		0,0				Design		#REF!		0		0		0,0				Design		#REF!		0		0		0,0				High-level Design		0,0		0		0		0,0
							Design Review		?????		0		0		0,0				Design Review		#REF!		0		0		0,0				Design Review		#REF!		0		0		0,0				Design Review		#REF!		0		0		0,0				Design Review		#REF!		0		0		0,0				HLDR		0,0		0		0		0,0
							Code		?????		0		0		0,0				Code		#REF!		0		0		0,0				Code		#REF!		0		0		0,0				Code		#REF!		0		0		0,0				Code		#REF!		0		0		0,0				Design		#REF!		0		0		0,0
							Code Review		?????		0		0		0,0				Code Review		#REF!		0		0		0,0				Code Review		#REF!		0		0		0,0				Code Review		#REF!		0		0		0,0				Code Review		#REF!		0		0		0,0				Design Review		#REF!		0		0		0,0
							Compile		?????		0		0		0,0				Compile		#REF!		0		0		0,0				Compile		#REF!		0		0		0,0				Compile		#REF!		0		0		0,0				Compile		#REF!		0		0		0,0				Code		#REF!		0		0		0,0
							Test		?????		0		0		0,0				Test		#REF!		0		0		0,0				Test		#REF!		0		0		0,0				Test		#REF!		0		0		0,0				Test		#REF!		0		0		0,0				Code Review		#REF!		0		0		0,0
							Total Development		?????		0		0		0,0				Total Development		#REF!		0		0		0,0				Total Development		#REF!		0		0		0,0				Total Development		#REF!		0		0		0,0				Total Development		#REF!		0		0		0,0				Compile		#REF!		0		0		0,0
							Test		#REF!		0		0		0,0
							Defects Removed					Defects Removed					Defects Removed					Defects Removed					Defects Removed					Total Development		#REF!		0		0		0,0
							Planning		?????		0		0		0,0				Planning		#REF!		0		0		0,0				Planning		#REF!		0		0		0,0				Planning		#REF!		0		0		0,0				Planning		#REF!		0		0		0,0
							Design		?????		0		0		0,0				Design		#REF!		0		0		0,0				Design		#REF!		0		0		0,0				Design		#REF!		0		0		0,0				Design		#REF!		0		0		0,0				Defects Removed
							Design Review		?????		0		0		0,0				Design Review		#REF!		0		0		0,0				Design Review		#REF!		0		0		0,0				Design Review		#REF!		0		0		0,0				Design Review		#REF!		0		0		0,0				Planning		#REF!		0		0		0,0
							Code		?????		0		0		0,0				Code		#REF!		0		0		0,0				Code		#REF!		0		0		0,0				Code		#REF!		0		0		0,0				Code		#REF!		0		0		0,0				High-level Design		0,0		0		0		0,0
							Code Review		?????		0		0		0,0				Code Review		#REF!		0		0		0,0				Code Review		#REF!		0		0		0,0				Code Review		#REF!		0		0		0,0				Code Review		#REF!		0		0		0,0				HLDR		0,0		0		0		0,0
							Compile		?????		0		0		0,0				Compile		#REF!		0		0		0,0				Compile		#REF!		0		0		0,0				Compile		#REF!		0		0		0,0				Compile		#REF!		0		0		0,0				Design		#REF!		0		0		0,0
							Test		?????		0		0		0,0				Test		#REF!		0		0		0,0				Test		#REF!		0		0		0,0				Test		#REF!		0		0		0,0				Test		#REF!		0		0		0,0				Design Review		#REF!		0		0		0,0
							Total Development		?????		0		0		0,0				Total Development		#REF!		0		0		0,0				Total Development		#REF!		0		0		0,0				Total Development		#REF!		0		0		0,0				Total Development		#REF!		0		0		0,0				Code		#REF!		0		0		0,0
							After Development				?????		?????					After Development				?????		?????					After Development				?????		?????					After Development				?????		?????					After Development				?????		?????					Code Review		#REF!		0		0		0,0
							Compile		#REF!		0		0		0,0
							Defect Removal Efficiency					Defect Removal Efficiency					Defect Removal Efficiency					Defect Removal Efficiency					Defect Removal Efficiency					Test		#REF!		0		0		0,0
							Def/Hr - DLDR		?????		?????		?????					Def/Hr - DLDR		#REF!		0,00		0,00					Def/Hr - DLDR		#REF!		0,00		0,00					Def/Hr - DLDR		#REF!		0,00		0,00					Def/Hr - DLDR		#REF!		0,00		0,00					Total Development		#REF!		0		0		0,0
							Def/Hr - CDR		?????		?????		?????					Def/Hr - CDR		#REF!		0,00		0,00					Def/Hr - CDR		#REF!		0,00		0,00					Def/Hr - CDR		#REF!		0,00		0,00					Def/Hr - CDR		#REF!		0,00		0,00					After Development				?????		?????
							Def/Hr - Compile		?????		?????		?????					Def/Hr - Compile		#REF!		0,00		0,00					Def/Hr - Compile		#REF!		0,00		0,00					Def/Hr - Compile		#REF!		0,00		0,00					Def/Hr - Compile		#REF!		0,00		0,00
							Def/Hr - Test		?????		?????		?????					Def/Hr - Test		#REF!		0,00		0,00					Def/Hr - Test		#REF!		0,00		0,00					Def/Hr - Test		#REF!		0,00		0,00					Def/Hr - Test		#REF!		0,00		0,00					Defect Removal Efficiency
							DRL(DLDR/UT)		?????		?????		?????					DRL(DLDR/UT)		0,00		0,00		0,00					DRL(DLDR/UT)		#REF!		0,00		0,00					DRL(DLDR/UT)		#REF!		0,00		0,00					DRL(DLDR/UT)		#REF!		0,00		0,00					Def/Hr - HLDR		0,00		0,00		0,00
							DRL(CDR/UT)		?????		?????		?????					DRL(CDR/UT)		0,00		0,00		0,00					DRL(CDR/UT)		#REF!		0,00		0,00					DRL(CDR/UT)		#REF!		0,00		0,00					DRL(CDR/UT)		#REF!		0,00		0,00					Def/Hr - DLDR		#REF!		0,00		0,00
							DRL(Compile/UT)		?????		?????		?????					DRL(Compile/UT)		0,00		0,00		0,00					DRL(Compile/UT)		#REF!		0,00		0,00					DRL(Compile/UT)		#REF!		0,00		0,00					DRL(Compile/UT)		#REF!		0,00		0,00					Def/Hr - CDR		#REF!		0,00		0,00
							Def/Hr - Compile		#REF!		0,00		0,00
							Def/Hr - Test		#REF!		0,00		0,00
							DRL(HLDR/UT)		#REF!		0,00		0,00
							DRL(DLDR/UT)		#REF!		0,00		0,00
							DRL(CDR/UT)		#REF!		0,00		0,00
							DRL(Compile/UT)		#REF!		0,00		0,00

## PROBE.XLM
Names	Formulas	Comments	Copyright 1996 James W. Over
	LRVariance	knownYs, knownXs, betaO, beta1
	#NOME?
	#NOME?
	#NOME?
	#NOME?
	#NOME?
LRVSum	0
	#NOME?
LRVy	#NOME?
LRVx	#NOME?
	#NOME?
	#NOME?
	#NOME?
	#NOME?

	PredictionRange	known Ys, known Xs, beta0, beta1, Xk, prcnt
	#NOME?
	#NOME?
	#NOME?	Copyright 1996 James W. Over
	#NOME?
	#NOME?
	#NOME?
	#NOME?
LRPRVar	#NOME?
LRPRStd	#NOME?
LRPRt	#NOME?
LRPRXavg	#NOME?
LRPRVSum	0
	#NOME?
LRPRVx	#NOME?
	#NOME?
	#NOME?
	#NOME?
	#NOME?

## Registro de tempo
Projeto	Fase	Data	Início	Interrupção	Término	Tempo	Comentários
ContadorLinhas	Planejamento	07/04/23	19:00:00		19:48:00	00:48:00
ContadorLinhas	Projeto	07/04/23	19:48:00		20:30:00	00:42:00
ContadorLinhas	Codificação	08/04/23	20:00:00	30 minutos	01:00:00	05:00:00
ContadorLinhas	Compilação					00:00:00
ContadorLinhas	Teste	09/04/2023	11:00:00		12:30:00	01:30:00
ContadorLinhas	Encerramento	09/04/2023	17:00:00		17:30:00	00:30:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00
						00:00:00

## Registro de erros
Projeto	Data	Número (Id)	Tipo	Fase de inserção	Fase de correção	Tempo para consertar	Referência para correção	Descrição
ContadorLinhas	08/04/2023		Lógico	Planejamento	Desenvolvimento	5 minutos		Erro de planejamento na lógica de contar linhas.
ContadorLinhas	08/04/2023		Sintaxe	Desenvolvimento	Desenvolvimento	3 minutos		Erro de sintaxe.
ContadorLinhas	08/04/2023		Sintaxe	Desenvolvimento	Desenvolvimento	10 minutos		Erro de sintaxe de particularidades do java.
ContadorLinhas	08/04/2023		Lógico	Desenvolvimento	Desenvolvimento	10 minutos		Contagem de linhas estava contando errado.
ContadorLinhas	08/04/2023		Lógico	Desenvolvimento	Desenvolvimento	5 minutos		Contagem de linhas printava em formato desordenado.

## SCMENUS
Project	Assignment	Process		Processes		Phases		PSP0		PSP0.1		PSP1		PSP1.1		PSP2		PSP2.1				Type	Description		Object Type	Object Type		Relative Size		Method
1	1A	PSP0		PSP0		PLAN		PLAN		PLAN		PLAN		PLAN		PLAN		PLAN				10	Documentation		C	Calculation		VS		A
2	2A	PSP0.1		PSP0.1		DLD		DLD		DLD		DLD		DLD		DLD		DLD				20	Syntax		D	Data		S		B
3	3A	PSP1		PSP1		DLDR		CODE		CODE		CODE		CODE		DLDR		DLDR				30	Build, Package		IO	Input/Output		M		C
4	4A	PSP1.1		PSP1.1		CODE		COMPILE		COMPILE		COMPILE		COMPILE		CODE		CODE				40	Assignment		L	Logic		L		D
5	5A	PSP2		PSP2		CR		TEST		TEST		TEST		TEST		CR		CR				50	Interface		S	Set-up		VL
6	6A	PSP2.1		PSP2.1		COMPILE		PM		PM		PM		PM		COMPILE		COMPILE				60	Checking		T	Text
7	7A	PSP2.1				TEST										TEST		TEST				70	Data
8	8A	PSP2.1				PM										PM		PM				80	Function
																						90	System
																						100	Environment

## ProjDB
Project	STU1 compatible		Time Summary		Defect Summary		Time by Phase					Defects Injected by Phase					Defects Removed by Phase					Size					Size Estimate		Time in Phase Est.
Number	Size N&C					PLAN		HLD		HLDR		DLD		DLDR		CODE		CR		COMPILE		TEST		PM		PLAN		HLD		HLDR		DLD		DLDR		CODE		CR		COMPILE		TEST		PM		PLAN		HLD		HLDR		DLD		DLDR		CODE		CR		COMPILE		TEST		PM		Base		Deleted		Modified		Added		Reused		New and Changed		Total		Total New Reuse		Object LOC		Pred. Intervals		Pred. Intervals		Project
Item:	EstLoc	ActLOC	EstMin	ActMin	EstDef	ActDef	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	UPI	LPI	UPI	LPI	Date	Language
1					0	0	0	0	0	0	0	0
2					0	0	0	0	0	0	0	0
3					0	0	0	0	0	0	0	0
4					0	0	0	0	0	0	0	0
5					0	0	0	0	0	0	0	0
6					0	0	0	0	0	0	0	0
7					0	0	0	0	0	0	0	0
8					0	0	0	0	0	0	0	0
9					0	0	0	0	0	0	0	0
10					0	0	0	0	0	0	0	0

		This worksheet holds the roll-up of actual time and defect data from the time log and defect log.

				This worksheet holds the roll-up of actual time and defect data from the time log and defect log. / Worksheet pdb uses references to this worksheet for actual time in phase, defects injected in phase, and defects removed in phase. / Worksheet Summary uses references to worksheet pdb for actual data.

## pdb
	Time in Phase					Defects Injected					Defects Removed
Program	Plan	HLD	HLDR	Design	DLDR	Code	CR	Compile	Test	PM	Plan	HLD	HLDR	Design	DLDR	Code	CR	Compile	Test	PM	Plan	HLD	HLDR	Design	DLDR	Code	CR	Compile	Test	PM
1	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0		0
2	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0		0
3	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0		0
4	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0		0
5	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0		0
6	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0		0
7	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0		0
8	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0		0
9	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0		0
10	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0		0
	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
				0					0					0

		This worksheet references worksheet ProjDB to get actual time and defect data. / Worksheet Summary uses references to this worksheet for actual time in phase, defects injected in phase, and defects removed in phase.

## Estimativa de tamanho e tempo
Tamanho do programa usado como base					Estimado		Efetivo
Tamanho inicial de base (B) =>					???
LOC apagadas (D) =>					???
LOC modificadas (M) =>					???
Adições feitas ao programa de base		Tipo		Métodos		Tamanho relativo		LOC		LOC

Total de adições ao programa de base (BA)					0,00		0
Novos módulos		Tipo		Métodos		Tamanho relativo		LOC	*	LOC

Total referente aos novos módulos (NO)					0,00		0
Módulos reutilizados					LOC		LOC

Total referente aos módulos reutilizados (R)					0,00		0

				Tamanho		Tempo
Previsão
Valor estimado				E = BA+NO+M				#VALOR!		???
Método de previsão selecionado					D		D
Parâmetro do método de regressão				B0				???		???
Parâmetro do método de regressão				B1				???		???
Estimativa de LOC novas ou alteradas				N = B0 + B1` * E				#VALOR!
Estimativa de total de LOC				T = N + B - D - M + R				#VALOR!
Estimativa de total de LOC para reutilização (sum of * LOC):					0,00
Estimativa de tempo total de desenvolvimento				Time = B0 + B1` * E					#VALOR!
Interface de previsão				Range
Limite superior de previsão				UPI = N + Range
Limite inferior de previsão				LPI = N - Range
Percentual do intervalo de previsão					0,70		70%
R^2

## Teste de software
Id	Objetivo	Dados de entrada	Condições de execução	Resultados esperados	Falhou/Passou	Resultado obtido (descrição)